## Sheet1
DISTRIBUTED DATABSE PROJECT PLANNING
TASK | UNDERTAKER | Start Date | End date
FINISH DOCUMENTS | ALL OF MEMBERS | 2018-05-21 | 2018-05-22
CREATING TABLE | H.VIỆT | 2018-05-22 | 2018-05-22
WRITE TRIGGER | G.BẢO | 2018-05-23 | 2018-05-26
WRITE PROCEDURE | M.HIẾU | 2018-05-23 | 2018-05-26
TESTING | H.VIỆT | 2018-05-26 | 2018-05-27